## Risk management log
Risk management log
Date risk raised | Exams cycle section | Risk | When could this happen? | Mitigation | Action | Action by whom | Action by when | Open/Closed | Risk reviewved | Date closed
XX/XX/XXXX | Planning | E.g. Invigilator numbers may be low for the upcoming exams series. | Summer XXXX | Ensure there are reserve invigilators who will provide cover in case of a shortfall. | 1. Conduct a review of available invigilators and their availability for the next exams series. 2. Use provisional timetable and estimated entry information to determine invigilator numbers required. 3. Identify where invigilators may be short. 4. Request permission to recruit additional invigilators. | Senior leader with responsibility for exams and assessment. Exams officer and HR officer. | Review of invigilation requirements and advert for new invigilators in local paper by end of February XXXX. | Closed | N/A | XX/XX/XXXX
XX/XX/XXXX | Exams day | E.g. Exams officer on sick leave absence during exams period. | Summer XXXX | Contingency plan in place to delegate tasks to other members of staff. | 1. Agree with members of staff to pick up responsibilities. 2. Document in a contingency plan. 3. Add to centre's exams policy. 4. Circulate and ensure it is easily accessible. 5. Calendar of exams tasks and key dates drawn up and available in staff room. | Senior leader with responsibility for exams and assessment. | Contingency plan to be published before the end of term. | Open | XX/XX/XXXX

## How to use this template
Risk management template
The risk management template is designed to help you examine potential risks relating to the administration and management of exams and how these might be managed and mitigated through forward planning and remedial actions. It is designed to provide a useful starting point for discussions with colleagues about the risks that might apply within your school or college.
How to use the risk management template
You should identify the risks that apply to your school and college and complete the necessary details in the risk management log. Examples of possible risks have been provided for illustrative purposes only. All mitigating actions should be approved by appropriate members of the senior leadership team to ensure that they are applicable and compatible with the policies and procedures of the school or college. A review of these should be undertaken on a regular basis to ensure that the strategies for managing the risk are still appropriate.
The template is accessible by selecting the 'Risk management log' worksheet tab below.