## SPRINT BACKLOG
SPRINT [NUMBER] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
US001 | As a call centre agent I need to be able to see the caller's previous tickets in their contact record. | Install standard contact record module | J Smith | Completed | 16 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Demo standard module and identify revised configuration. | J Smith | Completed |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete custom configuration as agreed in the demo. | J Smith | Completed |  | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | A a customer I need to be able to login to my account from any page on the website. | Install login widget on website. | F Dole | Completed | 48 | 0 | 0 | 5 | 7 | 2 | 8 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Apply customer branding. | J Smith | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
US003 | As a customer I need to be able to look up my address using my postcode. | Install contact page. | P Murphy | Completed | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
|  | Integrate postcode plugin to contact page. | P Murphy | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0
|  | Demo plugin to customer | J Smith | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
|  | Complete any changes required from Demo | J Smith | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
[5 empty] | 88 | 0.5 | 8 | 11 | 9 | 2 | 8 | 6 | 6 | 7 | 3 | 2 | 8 | 6 | 4 | 8

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Deployment Plan Template
Product Backlog Template
Project Management Templates